## Sheet1
Week | Task | Difficulty
2024-05-10 | Create a spreadsheet of project plan | Easy
| Create a trello board | Easy
| Create a Github repository | Easy
2024-05-15 | Replace the scaffolding code with the flask code and run in Cloud Shell | Medium
2024-05-19 | Set up GitHub Actions | Hard
| Add the GitHub Actions badge to the README | Medium
| Create the App Service in Azure | Medium
| Test the app running in Azure App Service | Medium
2024-05-26 | Set up the Azure DevOps pipeline | Hard
2024-06-02 | Create system architectural diagram | Medium
| Capture demonstrating key steps | Easy
| Update README file with full instructions of how to run the code | Medium
| Create a demo video and upload to YouTube | Medium
Goals
Submit project
Q3 plan | Submit the project
Yearly plan | Review the code and ensure it still works